## All
Sr.No | Date | Task | Task Description | From | Status | Done By | Start Date | Planned End Date | Actual End Date | Deployed By | Remarks | Delayed Reason (only if delayed) | Dependencies
Web_CR_1 | 2022-02-01 | Policy holder awareness | Policy holder awareness | Rajendra Singh Chhabra\Risk Management\Airoli | Completed | Farooq |  | 2022-02-03 | 2022-02-03 | Unique
Web_CR_2 | 2022-02-02 | PDF Changes on Site ( Download Section ) | PDF Changes on Site ( Download Section ) | Ananya Rath\Product Development\Navi Mumbai | Completed | Farooq |  | 2022-02-04 | 2022-02-04 | Unique
Web_CR_3 | 2022-02-03 | URGENT AUDIT REQUIREMENT: Link Addition in Our Website | URGENT AUDIT REQUIREMENT: Link Addition in Our Website | Padmaja Monalisa\Operations\Airoli | Completed | Farooq |  | 2022-02-04 | 2022-02-04 | Unique
Web_CR_4 | 2022-02-04 | SMS Whitelist for contact centre non operational | SMS Whitelist for contact centre non operational | Shoubhik Sinha\Customer Service\Airoli | Completed | Farooq |  | 2022-02-05 | 2022-02-05 | Unique
Web_CR_5 | 2022-02-05 | Added Title and Description | Added Title and Description | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq |  | 2022-02-07 | 2022-02-07 | Unique
Web_CR_6 | 2022-02-06 | Updation of Website - new Chairman on website. | Updation of Website - new Chairman on website. | Kanchan Parab\Company Secretary\HO - Mumbai | Completed | Farooq |  | 2022-02-07 | 2022-02-07 | Unique
Web_CR_7 | 2022-02-05 | PDF Changes on Site ( Download Section ) | PDF Changes on Site ( Download Section ) | Dipti Jaiprakashnarain Saxena | Completed | Farooq |  | 2022-02-07 | 2022-02-07 | Unique
Web_CR_8 | 2022-02-07 | Website upload | Website upload | Deepa Negi <deepa.negi@universalsompo.com> | Completed | Farooq |  | 2022-02-07 | 2022-02-07 | Unique
Web_CR_9 | 2022-02-07 | Upload of Stewardship Policy alongside public disclosure | Upload of Stewardship Policy alongside public disclosure | Soumya Shankar\Investments\HO-Mumbai <soumya.shankar@universalsompo.com> | Completed | Farooq |  | 2022-02-07 | 2022-02-07 | Unique
Web_CR_10 | 2022-02-08 | MD Photo alignment Issue | MD Photo alignment Issue | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq |  | 2022-02-09 | 2022-02-09 | Unique
Web_CR_11 | 2022-02-08 | update url in environment file https://universalsompo.com/USGIONLINE_PersonalAccidents/login.aspx | update url in environment file https://universalsompo.com/USGIONLINE_PersonalAccidents/login.aspx | Unique | Completed | Farooq |  | 2022-02-09 | 2022-02-09 | Unique
Web_CR_12 | 2022-02-08 | SMS Whitelist for contact centre non operational | SMS Whitelist for contact centre non operational | Dipti Jaiprakashnarain Saxena | Completed | Farooq |  | 2022-02-09 | 2022-02-09 | Unique
Web_CR_13 | 2022-02-08 | About Us ( MD Message Section Changes) Over Whatsapp | About Us ( MD Message Section Changes) Over Whatsapp | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq |  | 2022-02-09 | 2022-02-09 | Unique
Web_CR_14 | 2022-02-10 | Query 21 - Withdrawn products not displayed as per the guidelines on the website of the Insurer | Query 21 - Withdrawn products not displayed as per the guidelines on the website of the Insurer | Kasturi Desai\Product Development\Airoli | Completed | Unique |  | 2022-02-10 | 2022-02-10 | Unique
Web_CR_15 | 2022-02-10 | Query 19 - Data uploaded on the website of the Insurer | Query 19 - Data uploaded on the website of the Insurer | Kasturi Desai\Product Development\Airoli | Completed | Unique |  | 2022-02-11 | 2022-02-11 | Unique
Web_CR_16 | 2022-02-11 | Public Disclosure Q3 FY 2021-22 | Public Disclosure Q3 FY 2021-22 | Noopur Khatod\Deputy Manager-Finance & Accounts\HO-Mumbai <noopur.khatod@universalsompo.com> | Completed | Farooq / Unique |  | 2022-02-11 | 2022-02-11 | Unique
Web_CR_17 | 2022-02-19 | Change number in Grievance redressal list | Change number in Grievance redressal list | Shoubhik Sinha\Customer Service\Airoli | Completed | Farooq |  | 2022-02-21 | 2022-02-21 | Unique
Web_CR_18 | 2022-02-25 | Replacement of Proposal Form | Replacement of Proposal Form | Ananya Rath\Product Development\Navi Mumbai | Completed | Farooq |  | 2022-03-07 | 2022-03-07 | Unique
Web_CR_19 | 2022-03-08 | TRACK CLAIMS - WEBSITEQUERY - VINOD | TRACK CLAIMS - WEBSITEQUERY - VINOD | Shoubhik Sinha\Customer Service\Airoli | Completed | Farooq / Unique |  | 2022-03-10 | 2022-03-10 | Unique
Web_CR_20 | 2022-03-09 | Replace_Proposal Form | Replace_Proposal Form | Ananya Rath\Product Development\Navi Mumbai | Completed | Farooq |  | 2022-03-09 | 2022-03-09 | Unique
Web_CR_21 | 2022-03-17 | Replace_Proposal Form | Replace_Proposal Form | Kasturi Desai\Product Development\Airoli | Completed | Farooq |  | 2022-03-17 | 2022-03-17 | Unique
Web_CR_22 | 2022-03-31 | Website Update - Change Dupty CEO Profile and Message | Website Update - Change Dupty CEO Profile and Message | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq |  | 2022-04-01 | 2022-04-01 | Unique
Web_CR_23 | 2022-04-01 | Changes in About Page | Website Update - Remove both Hirokazu and Takahashi San. Shift Aditya Tibrewala in third no. and change his designation from Alternate Director to Nominee Director | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-04 | 2022-04-04 | 2022-04-04 | Unique
Web_CR_24 | 2022-04-06 | Changes in About Page | website change - Remove the Vishwanth V. Shenoy from the board of director list. | Komal Choudhary\Publicity\HO | Completed | Farooq | 2022-04-06 | 2022-04-07 | 2022-04-07 | Unique
Web_CR_25 | 2022-04-08 | Changes in About Page | website change - Nominee Director write Non-Executive Director - Aditya Tibrewala | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-11 | 2022-04-12 | 2022-04-12 | Unique
Web_CR_26 | 2022-04-13 | CSR Policy on Company Website: Kindly find attached herewith CSR policy to be uploaded on the link https://universalsompo.com/csr (CSR page of USGI website). | CSR Policy on Company Website: Kindly find attached herewith CSR policy to be uploaded on the link https://universalsompo.com/csr (CSR page of USGI website). | Hiral Nitin Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-04-13 | 2022-04-13 | 2022-04-13 | Farooq
Web_CR_27 | 2022-04-13 | USGI_134_Grievance Redressal Policy FY 2022-23 : upload the Board approved Grievance Redressal Policy | USGI_134_Grievance Redressal Policy FY 2022-23 : upload the Board approved Grievance Redressal Policy | Rita Thimmayya | Completed | Farooq | 2022-04-13 | 2022-04-13 | 2022-04-13 | Farooq
Web_CR_28 | 2022-04-13 | ATR status update for 47th PPC Meeting - Add FAQ to commercial individual pages | 27 commercial faq to be updated in website | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 2022-04-18 | 2022-04-29 | 2022-05-02 | Unique | 19/27 products has been updated on deployed. Other products will updated after CMS
Web_CR_29 | 2022-04-13 | Crop Claim Intimation Changes on Website | Crop Claim Intimation Changes on Website | Unique Jain | Completed | Farooq | 2022-04-13 | 2022-04-20 | 2022-04-30 | Unique
Web_CR_30 | 2022-04-13 | ATR status update for 47th PPC Meeting - Add motor claim FAQ to motor pages | Add motor insurance and motor claim faq to general faqs and claim process tab | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 2022-04-18 | 2022-04-25 | 2022-05-02 | Unique
Web_CR_31 | 2022-04-19 | Website Checklist | update the corporate agents list | Padmaja Monalisa\Operations\Airoli | Completed | Farooq | 2022-04-19 | 2022-04-19 | 2022-04-19 | Farooq
Web_CR_32 | 2022-04-20 | Website Checklist | Add "List of suspension / cancellation of agents" in download section | Padmaja Monalisa\Operations\Airoli | Completed | Farooq | 2022-04-20 | 2022-04-20 | 2022-04-20 | Unique
Web_CR_33 | 2022-04-22 | Insolvency & Bankruptcy Board of India Quiz | Add the given quiz gif in footer section location suggested by Anand and incorporate click event so once user click on GIF image in website it will open Brochure PDF for the same. | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-25 | 2022-04-29 | 2022-05-02 | Unique
Web_CR_34 | 2022-04-25 | Regarding Chennai II branch address DOOR NO wrongly mentioned in Office | update old address to this one "LAS Towers, Ground Floor, No-16, velacherry Main Road, Little Mount, Saidapet, Chennai-600015" | Padmaja Monalisa\Operations\Airoli | Completed | Unique | 2022-05-09 | 2022-05-09 | 2022-05-09 | Unique
Web_CR_35 | 2022-04-25 | Upload of AML Policy - USGI Website | update AML Policy PDF in Policies Page (https://universalsompo.com/policies) | Rajeshri Nakhwa\HR\HO – Mumbai | Completed | Farooq | 2022-04-25 | 2022-04-25 | 2022-04-25 | Unique
Web_CR_36 | 2022-04-25 | Revised Product Construct & Policy Schedule Format | List of changes: 1. Add banner on home landing page 2. Add “New Product Launched” button on health landing page 3. Updated Plan Highlights - health landing page 4. Updated “Features” - health landing page 5. Update 7 Plans in right plan section - complete healthcare page 6. Integrate lead generation API in health landing page after submitting following details – name, email, phone number, age 7. Show Thankyou pop after submitting lead generation form | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 2022-04-25 | 2022-04-27 | 2022-04-26 | Unique
Web_CR_37 | 2022-04-26 | Gallery | add Business Strategy Meet photo in gallary section present in about us and view all gallary page. | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-05-02 | 2022-05-06 | 2022-05-06 | Unique
Web_CR_38 | 2022-04-27 | Revised Product Construct & Policy Schedule Format | 8. Small the CHI Banner Card width 9. Add new CHI Logo in whole website 10. CHI lead generation should be mailed to contactus@universalsompo.com mail 11. Updates adds - on 12. show Plus, premier, executive first in compare plan 13. Remove Room rent, ICU charge from comparwe plan and add organ donar, daily cash in replacement 14. remove diagnostic test, spectales, contact lenses and replace it by cumulative bonus, and vaccination. 15. update following file for chi - policy wordings, prospectus, proposal form, premium chart, benefit chart 16. hide "get to know your policy better section" from CHI individual page 17.update setttlement ratio of individual pages 18. change name complete healthcare to New Complete Healthcare in 2 mins preview section. 19. update coverage and feature in 2 min preview section | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 2022-04-27 | 2022-04-30 | 2022-04-30
Web_CR_39 | 2022-04-27 | HDFC ERGO NAME APPEARING | HDFC ERGO Name was appearing in PDF Header so remove the name and update the new PDF | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-27 | 2022-04-27 | 2022-04-27 | Unique
Web_CR_40 | 2022-04-28 | Claim ratio | Update Claim Ration for the following helath products: Complete Healthcare Insurance Super Healthcare Insurance Arogya Sanjeevani Insurance Critical Illness Insurance Policy Corona Rakshak Policy Corona Kavach Policy | Inderpreet Singh\Health\Noida | Completed | Farooq | 2022-04-30 | 2022-05-02 | 2022-05-02 | Unique
Web_CR_41 | 2022-04-30 | ATR status update for 47th PPC Meeting | 20. Add FAQs to following individual health products: 1. Apat Suraksha 2. Arogya Sanjeevani Policy 3. Corona Kavach Policy 4. Critical Illness Policy 5. Hospital Daily Cash 6. Indian Bank Healthcare Plus 7. IOB Healthcare Plus 8. k Bank Healthcare Plus 9. Saral Suraksha Bima, USGI 10. Senior Citizen Health Insurance 11. Super Healthcare Insurance | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 31/04/2022 | 2022-05-06 | 2022-05-06 | Unique | 1. Apat Suraksha – Done 2. Arogya Sanjeevani Policy – Done 3. Corona Kavach Policy – Done 4. Critical Illness Policy – Done 5. Hospital Daily Cash– Not Done Reason: Saral Suraksha Bima FAQ is there in excel 6. Indian Bank Healthcare Plus – Done 7. IOB Healthcare Plus – Done 8. k Bank Healthcare Plus – Done 9. Saral Suraksha Bima, USGI – Done 10. Senior Citizen Health Insurance – Done 11. Super Healthcare Insurance – Not Done Reason: Arogya Sanjeevani Policy FAQ is there in excel
Web_CR_42 | 2022-04-30 | Uploading of documents on website | Add Add-ons to following commercial products: Universal Sompo- Bharat Sookshma Udyam Suraksha Universal Sompo - Bharat Laghu Udyam Suraksha Universal Sompo - Bharat Griha Raksha | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 31/04/2022 | 2022-05-02 | 2022-05-02 | Unique
Web_CR_43 | 2022-04-09 | Update on Website | Make the following changes on Website on the link https://universalsompo.com/csr 1. Remove name of Mr. V.V. Shenoy from CSR Committee Composition 2. Insert name of Mr. Aditya Tibrewala in place Mr. Hirokazu Yokomizo in CSR Committee Composition | Hiral Nitin Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-05-10 | 2022-05-10 | 2022-05-10 | Unique
Web_CR_44 | 2022-05-10 | Company Homepage | 1.Make the fixed because a user cannot find out which pdf is shown when he/she scrolls down. 2.The order of the product should be arranged by alphabetical order or LOB order for the user’s easy access. | Takashi Hasegawa\Global Marketing\Gurgaon | InProgress | Farooq | 2022-05-10 | 2022-05-10 | 2022-05-10 | Unique | 1.Make the fixed because a user cannot find out which pdf is shown when he/she scrolls down. - Done 2.The order of the product should be arranged by alphabetical order or LOB order for the user’s easy access. - On Hold . I have shared excel of alphabetical ordered products to check
Web_CR_45 | 2022-05-11 | Become Agent through USGI WEB SITE | on submitting become an agent form on page then mail should be send to 1. Aditya Chatwal 2. Himani Sharma 3. Dinesh Bhatt | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Unique / Farooq | 2022-05-10 | 2022-05-10 | 2022-05-10 | Unique
Web_CR_46 | 2022-05-15 | CHI Calculator |  | Health Underwriter | Completed | Unique
Web_CR_46 | 2022-05-16 | Become an agent | In the Become an agent, the following fields needs to be added and the lead should even flow to Bhaskar. Additional Fields 1. District 2. City 3. State 4. OTP verification for the mobile number | Avtar Singh Luthra\Head – Digital Technology\Airoli | InProgress | Farooq | 2022-04-23 | 2022-04-26 | 2022-05-26
Web_CR_47 | 2022-05-16 | Click to call from website | Integrate Ameyo Lead Api in Call me | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-05-16 | 2022-05-18
Web_CR_48 | 2022-05-17 | Latest CHI Renewal | Develop complete CHI renew design in current website | Unique Jain | InProgress | Farooq / Anand | 2022-05-18 | 2022-05-21
Web_CR_49 | 2022-05-18 | REQUEST A CALLBACK - WEBSITEQUERY - SHAILESHBHAI | route website call back requests to Fatima and Shoubhik | Avtar Singh Luthra\Head – Digital Technology\Airoli | InProgress | Unique
Web_CR_50 | 2022-05-24 | Insolvency & Bankruptcy Board of India Quiz | Remove the Quiz section from footer | Anand Rajkarne\Publicity\HO-Mumbai | Completed | Farooq | 2022-05-24 | 2022-05-26 | 2022-05-26
Web_CR_51 | 2022-05-24 | Public Disclosure Q3 Website | update the revised NL - 41 office information on our website for FY21-22 Q3 | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-05-24 | 2022-05-24 | 2022-05-24
Web_CR_52 | 2022-05-24 | Jack Hoax - Hosting on web | Upload a Jack Hoax on website and share a link | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-05-24 | 2022-05-24 | 2022-05-24
Web_CR_53 | 2022-05-24 | Update on Website | Added two new directors 1. Mr. Vincent Ng Lui Kwang – Alternate Director 2. Mr. Mudit Gupat - Alternate Director | Anand Rajkarne\Publicity\HO-Mumbai | Completed | Farooq | 2022-05-24 | 2022-05-26 | 2022-05-26
Web_CR_54 | 2022-05-24 | upload image on server | 24-05-2022.png image in emailer folder | Anand Rajkarne\Publicity\HO-Mumbai | Completed | Farooq | 2022-05-24 | 2022-05-24 | 2022-05-24
Web_CR_55 | 2022-05-25 | Update on Website | Update two files on website: 1. CSR Action Plan 2022-23 2. Notice of resignation of Directors | Hiral Nitin Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-05-25 | 2022-05-25 | 2022-05-25
Web_CR_56 | 2022-05-26 | Policy update on website | replace the attached file of Remuneration Policy | Hiral Nitin Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-05-26 | 2022-05-26 | 2022-05-26
Web_CR_57 | 2022-05-26 | Add State and City Field in CHI Lead Form | Add State and City Field in CHI Lead Form | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-05-26 | 2022-05-26 | 2022-05-26
Web_CR_58 | 2022-05-30 | State / City / Pincode | Add State, City and Pincode Field in CHI Lead Form and save in DB | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-05-30 | 2022-06-01 | 2022-06-01
Web_CR_59 | 2022-06-03 | Become Agent through USGI WEB SITE | mails are not received to receivers | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-06-03 | 2022-06-03 | 2022-06-03
Web_CR_60 | 2022-06-06 | Public Disclosure Q4 FY 21-22 |  | Noopur Khatod\Manager-Finance & Accounts\HO-Mumbai | Completed | Unique
| 2022-06-12 | CHI Calculator Payment gateway integration |  | Health Underwriter | InProgress | Unique
Web_CR_61 | 2022-06-16 | Annual Return on Website | Kindly make a new tab beside Annual Report with heading Annual Return on link https://universalsompo.com/secretarial Upload the attached file for FY 2020-21 in the Annual Return tab. | Hiral Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-06-21 | 2022-06-22 | 2022-06-22
Web_CR_62 | 2022-06-20 | Upload of Stewardship Policy alongside public disclosure | kindly upload the attached files on our site under “Public Disclosure” section under the subsection “For Financial year 2021-22” under the heading of “Stewardship Activity” as under: • File name “USGIC – Q4FY2022 - General Meeting Voting” under “Stewardship Activity – Q4” • File name “USGIC - FY2022 - General Meeting Voting” under “Stewardship Activity – FY2022” | Soumya Shankar\Investments\HO-Mumbai | Completed | Farooq | 2022-06-21 | 2022-06-22 | 2022-06-22
Web_CR_63 | 2022-06-21 | TPA Servicing- column to remove | Kindly remove/ hide Public disclosure of Quantitative & Qualitative Parameters column from the https://www.universalsompo.com/claims/tpa-servicing-group-health-insurance page. | Inderpreet Singh\Health\Noida | Completed | Farooq | 2022-06-22 | 2022-06-22 | 2022-06-22
Web_CR_64 | 2022-06-21 | Updation required- https://www.universalsompo.com/claims/claims-process | Following changes are required in the section ‘Follow below steps to avail cashless facility…..’ Step I: change toll free number to 1800 200 4030 Please replace the following line in Step IV Step IV: Hospital verifies the patient details and sends duly filled Cashless Request Form by mail to Universal Sompo Health team at healthserve@universalsompo.com | Inderpreet Singh\Health\Noida | Completed | Farooq | 2022-06-22 | 2022-06-22 | 2022-06-22
Web_CR_65 | 2022-06-23 | Redirection to CHI Journey | Implement the redirection from Website CHI pages to below CHI journey as per our discussion. https://www.universalsompo.com/CompleteHealthCare | Unique Jain\Senior Software Developer\Airoli | Completed | Farooq | 2022-06-23 | 2022-06-23 | 2022-06-23
Web_CR_66 | 2022-06-23 | USGI Website Checklist | we need to update this on the website Step1: The customer needs to send email from registered emailid to our helpline center contactus@universalsompo.com. Step2: The customer can place the request for physical copy of the policy to be delivered at the registered address by mentioning policy number in the email. Step3: The physical copy of the policy will be sent by registered mail/courier to the customer under intimation to the customer by email. | Aashi Saraf <aashi.saraf@universalsompo.com> | Completed | Farooq | 2022-06-23 | 2022-06-23 | 2022-06-23
Web_CR_67 | 2022-06-23 | WACode and WAAppcode | Kindly use below WACode and WAAppCode for CHI product in prod and UAT respectively. For UAT: WACode: 20000001 WAAppCode : 30000011 For Prod: WACode : 20000001 WAAppCode : 30000007 | Nagesh Chavan\Tech & Innovation\Airoli | Completed | Farooq | 2022-06-23 | 2022-06-23 | 2022-06-23
Web_CR_68 | 2022-06-23 | AGM Notice on Website | upload the attached AGM notice on Website on link https://universalsompo.com/secretarial The attached file should be uploaded beside the file “Transcript of 14th AGM” | Hiral Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-06-24 | 2022-06-24 | 2022-06-24
Web_CR_69 | 2022-06-23 | Updation required- https://www.universalsompo.com/claims/claims-process | changes in the section ‘Follow below steps to lodge your Health Insurance……’ Step I: Change toll free number to 1800 200 4030 Step IV: Change the address: Universal Sompo General Insurance Company Limited Health Claims Management Office, 1st Floor, Plot No. C 56 A/13, Block C, Sector- 62, Noida, Uttar Pradesh- 201309 | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-06-24 | 2022-06-24 | 2022-06-24
Web_CR_70 | 2022-06-24 | Website Checklist | Update Revised Motor TP on website | NarendraSingh BaljitSingh Lote\Head – Retail Lines Business\Airoli | Completed | Farooq | 2022-06-24 | 2022-06-24 | 2022-06-24
Web_CR_71 | 2022-06-24 | Website Review_Q1 | Upload the following files on website 1. AML Policy 2. Agenda 12 POSH Policy 3. Whistle Blower Policy | Rajeshri Nakhwa\HR\HO – Mumbai | Completed | Farooq | 2022-06-24 | 2022-06-24 | 2022-06-24
Web_CR_72 | 2022-06-27 | Upload of Documents on website under Commercial Section | Update Commercial products - Proposal Form | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-06-30 | 2022-06-30 | 2022-06-30
Web_CR_73 | 2022-06-27 | Hospital Details update- Website | added latitude and longitude and update on database | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq / Unique | 2022-06-29 | 2022-06-29 | 2022-06-29
Web_CR_74 | 2022-06-27 | Website Glitch | This is to notify you that we have identified glitch on our website. FAQs tab is unsuitable. If we scroll to FAQs then it occurs under “Reviews” tab. Please find screenshot below for your reference and take necessitate action. | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-06-30 | 2022-07-01 | 2022-07-01
Web_CR_75 | 2022-06-27 | ATR status update for 47th PPC Meeting | We have made some changes in the FAQs which needs to be updated on website under Health Product. Please do the needful and once the same has been done kindly update on the same. | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-06-30 | 2022-07-01 | 2022-07-01
Web_CR_76 | 2022-06-29 | Proposal forms for Website | update the health proposal form | Kasturi Desai\Product Development\Airoli <kasturi.desai@universalsompo.com> | Completed | Farooq | 2022-06-29 | 2022-06-29 | 2022-06-29
Web_CR_77 | 2022-07-04 | Proposal Form small corrections | Re upload few chi proposal form: 1. CHI 2. Indian Bank Healthcare Plus 3. K Bank 4. IOB Bank | Kasturi Desai\Product Development\Airoli <kasturi.desai@universalsompo.com> | Completed | Farooq | 2022-07-04 | 2022-07-04 | 2022-07-04
Web_CR_78 | 2022-07-04 | RE: Proposal Form small corrections | Re upload few chi proposal form: 1. Surva Vidharti bima yojana 2. Pravasi bharatiya bima yojana 3. Swarna Garmin Bima yojana | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-07-04 | 2022-07-04 | 2022-07-04
Web_CR_79 | 2022-07-04 | Change Travel product from other to health (over call) | Change Travel insurance and Domestic travel insurance from other section of download to health | Kasturi Desai\Product Development\Airoli <kasturi.desai@universalsompo.com> | Completed | Farooq | 2022-07-04 | 2022-07-04 | 2022-07-04
Web_CR_80 | 2022-07-04 | RE: ATR status update for 47th PPC Meeting | 1) Please find attached FAQ’s of Health Products which needs to be uploaded on website. 2) Also note that for Janta Personal Accidental page FAQs tab is missing. 3) For Loan Secure Insurance Policy, we need to replace the uploaded prospectus and Rate chart with the attached PDF. | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-07-05 | 2022-07-06 | 2022-07-07 |  |  | late deployed by unique
Web_CR_81 | 2022-07-06 | FW: Company Website Updation: List of Corporate agents |  | Padmaja Monalisa\Operations\Airoli <padmaja.monalisa@universalsompo.com> | Completed | Farooq | 2022-07-06 | 2022-07-06 | 2022-07-06
web_CR_82 | 2022-07-07 | Public Disclosures -Mar 22(Q4) |  | Unique Jain | Completed | Farooq | 2022-07-07 | 2022-07-07 | 2022-07-07
Web_CR_83 | 2022-07-08 | FW: Upload of Documents on website under Commercial Section. | Update uat observation of commercial phase 1 file uploads - policy wordings, prospectus, proposal form, clauses, adds on | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-07-12 | 2022-07-15 | 2022-07-15
Web_CR_84 | 2022-07-08 | FW: Upload of Documents on website under Commercial Section. | Update uat observation of commercial phase 2 file uploads - policy wordings, prospectus, proposal form, clauses, adds on | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-07-12 | 2022-07-15 | 2022-07-15
Web_CR_85 | 2022-07-12 | RE: Proposal Form small corrections | Request you to re-upload the attached proposal form on website. There are few changes made in the proposal form. | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-07-12 | 2022-07-14 | 2022-07-12
Web_CR_86 | 2022-07-12 | FW: Upload of Documents on website under Commercial Section. | Update uat observation of commercial phase 3 file uploads - policy wordings, prospectus, proposal form, clauses, adds on | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-07-12 | 2022-07-15 | 2022-07-15
Web_CR_87 | 2022-07-12 | FW: BECOME AN AGENT - WEBSITEQUERY - HIMANI TESTING
Web_CR_88 | 2022-07-14 | RE: Upload of Documents on website under Commercial Section. | Phase 1 observations | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-07-14 | 2022-07-15 | 2022-07-15
Web_CR_89 | 2022-07-14 | FW: WEBSITEQUERY
Web_CR_90 | 2022-07-14 | FW: website - banca tab | Update the following changes: Also, Network Hospital has increased to 5604. PRODUCT WISE SETTTETMENT Settlement Ratio INDIAN BANK HEALTH CARE PLUS INSURANCE 97% IOB HEALTHCARE PLUS INSURANCE POLICY 96% K BANK HEALTH CARE PLUS INSURANCE 97% | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-07-14 | 2022-07-15 | 2022-07-15
Web_CR_91 | 2022-07-15 | RE: Upload of Documents on website under Commercial Section. | Replace the trade credit proposal form and Employees compensation form still not replace Also add-ons and policy wordings mentioned below have not been uploaded | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-07-15 | 2022-07-15 | 2022-07-15
Web_CR_92 | 2022-07-19 | FW: Duplicate forms- Health | remove the duplicate health forms from claims form | Inderpreet Singh\Health\Noida | Completed | Farooq | 2022-07-19 | 2022-07-21 | 2022-07-21
Web_CR_93 | 2022-07-25 | Public Disclosure NL Q4 FY 21-22 | Update NL-37 form in Q4 21-22 | Noopur Khatod\Manager-Finance & Accounts\HO-Mumbai <noopur.khatod@universalsompo.com> | Completed | Farooq | 2022-07-25 | 2022-07-25 | 2022-07-25
Web_CR_94 | 2022-07-25 | Replace Prospectus on website - Karnataka Bank Health Care Plus | Replace K bank health care prospectus | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-07-25 | 2022-07-25 | 2022-07-25
Web_CR_95 | 2022-07-28 | List of Approved Products_USGI | update our Website with a tab for “Product List”. | Kasturi Desai\Product Development\Airoli <kasturi.desai@universalsompo.com> | Completed | Farooq | 2022-07-28 | 2022-07-30 | 2022-08-02
Web_CR_96 | 2022-07-28 | FW: BECOME AN AGENT - WEBSITEQUERY - HIMANI TESTING | design and develop complete become and agent journey | Himani Sharma\Marketing\HO - Mumbai <Himani.sharma@universalsompo.com> | Completed | Farooq | 2022-07-30 | 2022-08-05
Web_CR_97 | 2022-08-01 | RE: Upload of Documents on website under Commercial Section. | replace the proposal forms on website with the attached in the commercial section | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-08-02 | 2022-08-04 | 2022-08-02
Web_CR_98 | 2022-08-02 | RE: Upload of Documents on website under Commercial Section. | replace the proposal forms on website with the attached in the commercial section | Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Farooq | 2022-08-03 | 2022-08-04 | 2022-08-04
Web_CR_99 | 2022-08-02 | FW: CHI prospectus & Wordings | change prospectua and policy wordings | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-08-03 | 2022-08-04 | 2022-08-04
Web_CR_100 | 2022-08-03 | Update on Website | add imran amin as additional non-executive director after MD sir | Hiral Parekh\Legal & Compliance\HO-Mumbai <hiral.parekh@universalsompo.com> | Completed | Farooq | 2022-08-03 | 2022-08-04 | 2022-08-04
Web_CR_101 | 2022-08-04 | Website Review - Covid 19 | add Covid 19 section on website | Kasturi Desai\Product Development\Airoli <kasturi.desai@universalsompo.com> | Completed | Farooq
Web_CR_102 | 2022-08-05 | RE: CHI proposal form | update chi proposal form | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-08-08 | 2022-08-08 | 2022-08-08
Web_CR_103 | 2022-08-08 | FW: Website Review_Q1 |  | Aashi Saraf <aashi.saraf@universalsompo.com> | Completed | Farooq | 2022-08-26 | 2022-08-26 | 2022-08-26
Web_CR_104 | 2022-08-10 | FW: Company Website Updation: List of Corporate agents | update the list of Corporate Agents and List of Terminated/Blacklisted agents in our website. | Padmaja Monalisa\Operations\Airoli <padmaja.monalisa@universalsompo.com> | Completed | Farooq | 2022-08-10 | 2022-08-10 | 2022-08-10
Web_CR_105 | 2022-08-11 | remove the link | Remove / block this link from website either by showing 404 error or redirecting it to home page https://www.universalsompo.com/Blog/ | Avtar Singh Luthra\Head – Digital Technology\Airoli | Completed | Farooq | 2022-08-11 | 2022-08-11 | 2022-08-11
Web_CR_106 | 2022-08-11 | Public Disclosure Q1 FY 2022-23 |  | Noopur Khatod\Manager-Finance & Accounts\HO-Mumbai <noopur.khatod@universalsompo.com> | Completed | Farooq | 2022-08-11 | 2022-08-12 | 2022-08-12
Web_CR_107 | 2022-08-12 | RE: CHI prospectus & Wordings |  | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Farooq | 2022-08-12 | 2022-08-12 | 2022-08-12
Web_CR_108 | 2022-08-12 | FW: PA Claim FAQ's | Add faqs for Motor and PA | Zohrab Sayyed\Claims\Navi-Mumbai <zohrab.sayyed@universalsompo.com> | Completed | Farooq | 2022-08-22 | 2022-08-22 | 2022-08-26
Web_CR_109 | 2022-08-18 | FW: Upload of Stewardship Policy alongside public disclosure | upload the attached files on our site under “Public Disclosure” section under the subsection “For Financial year 2022-23” under the heading of “Stewardship Activity” as under: • File name “USGIC – Q1FY2023 - General Meeting Voting” under “Stewardship Activity – Q1” | Soumya Shankar\Investments\HO-Mumbai <soumya.shankar@universalsompo.com> | Completed | Farooq | 2022-08-18 | 2022-08-18 | 2022-08-18
Web_CR_110 | 2022-08-19 | RE: Update on Website | remove details of Mr. Vincent Ng Lui Kwang (Alternate Director) from Company Website | : Hiral Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-08-22 | 2022-08-22 | 2022-08-22
Web_CR_111 | 2022-08-23 | FW: Cyber Insurance Policy- Retail - Website development |  | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Farooq | 2022-08-25 | 2022-08-30
Web_CR_112 | 2022-08-23 | List of product_ Documents to be uploaded on website |  | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Komal | 2022-08-23 | 2022-08-24 | 2022-08-24
Web_CR_113 | 2022-08-25 | Fw: Bancassurance FAQ : English, HIndi, Tamil to Telgu | update bancassurance claim faqs | Zohrab Sayyed\Claims\Navi-Mumbai <zohrab.sayyed@universalsompo.com> | Completed | Farooq | 2022-08-26 | 2022-08-26 | 2022-08-26
Web_CR_114 | 2022-08-25 | FW: Placement of IRDAI’s Tagline Contest banner on Insurers, Insurance Intermediaries websites. | add promotional IRDAI tagline contest in footer | : Komal Malani\Branding & Corporate Communications\HO - Mumbai | Completed | Farooq | 2022-08-26 | 2022-08-26 | 2022-08-26
Web_CR_115 | 2022-08-25 | RE: Update on Website | Secretarial tab – there would be 14th AGM Transcript. Please upload this file next to it | Aarti Kamath\Company Secretary\HO-Mumbai <aarti.kamath@universalsompo.com> | Completed | Farooq | 2022-08-26 | 2022-08-26 | 2022-08-26
Web_CR_116 | 2022-08-26 | FW: Corporate Agent details to be updated in USGIC FY 22-23 | As discussed, as per Compliance team in our USGIC web site Corporate Agent details to be placed as per IRDAI norms once updated please reply for the same. In resources section – Label Name - Corporate Agent details | FW: Corporate Agent details to be updated in USGIC FY 22-23 | Completed | Farooq | 2022-08-26 | 2022-08-27 | 2022-08-26
Web_CR_117 | 14/9/2022 | Emergency Contact on Website | Request you to replace Shoubhik’s name with mine in Emergency Contact. Please find the link: https://www.universalsompo.com/resourse-grievance-redressal | Rita Thimmayya <Rita.Thimmayya@universalsompo.com> | completed | Komal | 14/9/2022 | 14/9/2022 | 14/9/2022
Web_CR_118 | 14/9/2022 | Prospectus - Travel Insurance | Prospectus of Retail Travel. | Kasturi Desai\Product Development\HO - Mumbai <kasturi.desai@universalsompo.com> | Completed | Komal | 16/9/2022 | 16/9/2022 | 16/9/2022
Web_CR_119 | 15/9/2022 | Cyber Insurance Policy- Retail - Website development | Retail file added in commercial | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Komal | 15/9/2022 | 15/9/2022 | 15/9/2022
Web_CR_120 | 21/9/2022 | EGM notice on website | 6th EGM notice is uploaded on website | Hiral Parekh\Legal & Compliance\HO-Mumbai <hiral.parekh@universalsompo.com> | Completed | Komal | 21/9/2022 | 21/9/2022 | 21/9/2022
Web_CR_121 | 26/9/2022 | Cyber Insurance Policy- Retail - Website development Commercial proposal form | • clauses for policy, Contractor's Plant & Machinery Insurance ( Retail) • Prospectus and proposal form for policy Money Insurance Policy- Retail- Retail • Proposal form for Brackish Water Prawn Insurance Policy (Commercial) • Proposal form for Inland Fresh Water Fisheries Policy (Commercial)  Brackish Water Prawn Insurance Policy- Commercial Proposal form has been uploaded. Please upload the attached proposal form of Retail | : Dipti Saxena <dipti.saxena@universalsompo.com | Completed | Komal | 26/9/22 | 26/9/22 | 26/9/22
Web_CR_122 | 28/9/2022 | Covid-19 Assistance page create | Support in added card covid 19 assistance. And developed covid 19 assistance page | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 28/9/22 | 28/9/22 | 28/9/22
Web_CR_123 | 29/9/2022 | Janata Personal Accident Insurance Policy(Long Term) | Janata Personal Accident Insurance Policy(Long Term) pdf added in health | Mini Mishra\Product Development\Navi Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 29/9/22 | 29/9/22 | 29/9/22
Web_CR_124 | 2022-10-13 | RE: Prospectus- Website | While updating the prospectus on website you have uploaded the same under policy wording of Sampoorna Suraksha Bima (Micro Insurance Package Policy). Please change it asap with the attached policy wording | Mini Mishra\Product Development\Head Office - Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 2022-10-13 | 2022-10-13 | 2022-10-13
Web_CR_125 | 2022-10-28 | website changes(chi) | CHI show and hide toggle button remove | gaytri | Completed | Komal | 2022-10-27 | 2022-10-27 | 2022-10-27
Web_CR_126 | 2022-10-31 | Website Upload | Please upload the attached documents on website under Commercial section Please replace the documents of Cattle insurance Policy Pls make new line item for Cyber as Cyber Insurance Policy- Retail and upload the documents under that. | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Komal | 2022-10-29 | 2022-10-31 | 2022-10-31
Web_CR_127 | 2022-10-31 | Clauses to be updated- | Kindly replace the attached clauses with the clauses that are updated in Contractors All Risk Insurance Under commercial section | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Komal | 2022-10-31 | 2022-10-31 | 2022-10-31 | komal
Web_CR_128 | 2022-10-31 | RE: Website Updation: List of Corporate agents | Please help update above attached PDFs in our website. https://universalsompo.com/resources-downloads | : Padmaja Monalisa\Operations\Airoli <padmaja.monalisa@universalsompo.com> | Completed | Komal | 2022-10-31 | 2022-10-31 | 2022-10-31 | komal
Web_CR_129 | 2022-10-31 | Re: Policy Wording - Website | Please find last policy wording of Group Health Insurance. In total I have shared 13 products for the replacement. Kindly confirm once uploaded on urgent basis. | Mini Mishra\Product Development\Head Office - Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 2022-10-31 | 2022-10-31 | 2022-10-31 | komal
Web_CR_130 | 2022-11-02 | FW: Public Disclosure Mar 22 | public disclosure NL 43 for Q4 of FY 21-22 | Avtar Luthra\Head- Digital Technology\Airoli <avtarsingh.luthra@universalsompo.com> | Completed | Komal | 2022-11-02 | 2022-11-02 | 2022-11-02 | komal
Web_CR_131 | 2022-11-11 | RE: Display of e banner on website on occasion of Bima Lokpal Day 2022- 11th November 2022 | Pls display the attached banner on the website. Pls confirm once done. | Anand Rajkarne\Publicity\HO-Mumbai <anand.rajkarne@universalsompo.com>; |  |  | 2022-11-11 | 2022-11-11 | 2022-11-11 | komal
Web_CR_132 | 2022-11-02 | RE: Prospectus - Website | Request you to upload attached Prospectus of listed products on website: 1) Pravasi Bhartiya Bima Yojana 2) Swarna Gramin Bima Yojana – Individual 3) Swarna Gramin Bima Yojana - Group | From: Mini Mishra\Product Development\Head Office - Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 2022-11-02 | 2022-11-02 | 2022-11-02 | komal
Web_CR_135 | 2022-11-14 | Corrupt file on website | The uploaded file on website under premium chart for Karnataka Bank Health Care Plus is corrupted and we are unable to open the downloaded file. Request you to kindly look into it and make the file accessible on website. | Mini Mishra\Product Development\Head Office - Mumbai <Mini.Mishra@universalsompo.com> | Completed | Komal | 2022-11-14 | 2022-11-14 | 2022-11-14 | Komal
Web_CR_136 | 2022-11-14 | RE: Website upload | Kindly replace the existing documents with the attached documents for the below products under Motor Section. Pls call for any clarification. Sr No Name of the Product UIN 7 Motor Passenger Carrying Vehicle IRDAN134RP0008V02200809 8 Miscellaneous Vehicle IRDAN134RP0010V02200809 10 Motor Private Car Policy IRDAN134RP0004V02200708 | Dipti Saxena <dipti.saxena@universalsompo.com> | Completed | Komal | 2022-11-14 | 2022-11-14 | 2022-11-14 | Komal

## Monthly
Sr.No | Date | Task | Task Description | From | Status | Done By | Start Date | Planned End Date | Actual End Date | Deployed By | Remarks | Delayed Reason (only if delayed) | Dependencies
1 | 2022-04-01 | Changes in About Page | Website Update - Remove both Hirokazu and Takahashi San. Shift Aditya Tibrewala in third no. and change his designation from Alternate Director to Nominee Director | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-04 | 2022-04-04 | 2022-04-04 | Unique
2 | 2022-04-06 | Changes in About Page | website change - Remove the Vishwanth V. Shenoy from the board of director list. | Komal Choudhary\Publicity\HO | Completed | Farooq | 2022-04-06 | 2022-04-07 | 2022-04-07 | Unique
3 | 2022-04-08 | Changes in About Page | website change - Nominee Director write Non-Executive Director - Aditya Tibrewala | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-11 | 2022-04-12 | 2022-04-12 | Unique
4 | 2022-04-13 | CSR Policy on Company Website | CSR Policy on Company Website: Kindly find attached herewith CSR policy to be uploaded on the link https://universalsompo.com/csr (CSR page of USGI website). | Hiral Nitin Parekh\Legal & Compliance\HO-Mumbai | Completed | Farooq | 2022-04-13 | 2022-04-13 | 2022-04-13 | Farooq
5 | 2022-04-13 | USGI_134_Grievance Redressal Policy FY 2022-23 : upload the Board approved Grievance Redressal Policy | USGI_134_Grievance Redressal Policy FY 2022-23 : upload the Board approved Grievance Redressal Policy | Rita Thimmayya | Completed | Farooq | 2022-04-13 | 2022-04-13 | 2022-04-13 | Farooq
6 | 2022-04-13 | ATR status update for 47th PPC Meeting - Add FAQ to commercial individual pages | 27 commercial faq to be updated in website | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 2022-04-18 | 2022-04-29 | 2022-05-02 | Unique | 19/27 products has been updated on deployed. Other products will updated after CMS
7 | 2022-04-13 | Crop Claim Intimation Changes on Website | Crop Claim Intimation Changes on Website | Unique Jain | Completed | Farooq | 2022-04-13 | 2022-04-20 | 2022-04-30 | Unique
8 | 2022-04-13 | ATR status update for 47th PPC Meeting - Add motor claim FAQ to motor pages | Add motor insurance and motor claim faq to general faqs and claim process tab | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 2022-04-18 | 2022-04-25 | 2022-05-02 | Unique
9 | 2022-04-19 | Website Checklist | update the corporate agents list | Padmaja Monalisa\Operations\Airoli | Completed | Farooq | 2022-04-19 | 2022-04-19 | 2022-04-19 | Farooq
10 | 2022-04-20 | Website Checklist | Add "List of suspension / cancellation of agents" in download section | Padmaja Monalisa\Operations\Airoli | Completed | Farooq | 2022-04-20 | 2022-04-20 | 2022-04-20 | Unique
11 | 2022-04-22 | Insolvency & Bankruptcy Board of India Quiz | Add the given quiz gif in footer section location suggested by Anand and incorporate click event so once user click on GIF image in website it will open Brochure PDF for the same. | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-25 | 2022-04-29 | 2022-05-02 | Unique
12 | 2022-04-25 | Regarding Chennai II branch address DOOR NO wrongly mentioned in Office | update old address to this one "LAS Towers, Ground Floor, No-16, velacherry Main Road, Little Mount, Saidapet, Chennai-600015" | Padmaja Monalisa\Operations\Airoli | Completed | Unique | 2022-05-09 | 2022-05-09 | 2022-05-09 | Unique
13 | 2022-04-25 | Upload of AML Policy - USGI Website | update AML Policy PDF in Policies Page (https://universalsompo.com/policies) | Rajeshri Nakhwa\HR\HO – Mumbai | Completed | Farooq | 2022-04-25 | 2022-04-25 | 2022-04-25 | Unique
14 | 2022-04-25 | Revised Product Construct & Policy Schedule Format | List of changes: 1. Add banner on home landing page 2. Add “New Product Launched” button on health landing page 3. Updated Plan Highlights - health landing page 4. Updated “Features” - health landing page 5. Update 7 Plans in right plan section - complete healthcare page 6. Integrate lead generation API in health landing page after submitting following details – name, email, phone number, age 7. Show Thankyou pop after submitting lead generation form | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 2022-04-25 | 2022-04-27 | 2022-04-26 | Unique
15 | 2022-04-26 | Gallery | add Business Strategy Meet photo in gallary section present in about us and view all gallary page. | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-05-02 | 2022-05-06 | 2022-05-06 | Unique
16 | 2022-04-27 | Revised Product Construct & Policy Schedule Format | 8. Small the CHI Banner Card width 9. Add new CHI Logo in whole website 10. CHI lead generation should be mailed to contactus@universalsompo.com mail 11. Updates adds - on 12. show Plus, premier, executive first in compare plan 13. Remove Room rent, ICU charge from comparwe plan and add organ donar, daily cash in replacement 14. remove diagnostic test, spectales, contact lenses and replace it by cumulative bonus, and vaccination. 15. update following file for chi - policy wordings, prospectus, proposal form, premium chart, benefit chart 16. hide "get to know your policy better section" from CHI individual page 17.update setttlement ratio of individual pages 18. change name complete healthcare to New Complete Healthcare in 2 mins preview section. 19. update coverage and feature in 2 min preview section | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 2022-04-27 | 2022-04-30 | 2022-04-30
17 | 2022-04-27 | HDFC ERGO NAME APPEARING | HDFC ERGO Name was appearing in PDF Header so remove the name and update the new PDF | Komal Choudhary\Publicity\HO - Mumbai | Completed | Farooq | 2022-04-27 | 2022-04-27 | 2022-04-27 | Unique
18 | 2022-04-28 | Claim ratio | Update Claim Ration for the following helath products: Complete Healthcare Insurance Super Healthcare Insurance Arogya Sanjeevani Insurance Critical Illness Insurance Policy Corona Rakshak Policy Corona Kavach Policy | Inderpreet Singh\Health\Noida | Completed | Farooq | 2022-04-30 | 2022-05-02 | 2022-05-02 | Unique
19 | 2022-04-30 | ATR status update for 47th PPC Meeting | 20. Add FAQs to following individual health products: 1. Apat Suraksha 2. Arogya Sanjeevani Policy 3. Corona Kavach Policy 4. Critical Illness Policy 5. Hospital Daily Cash 6. Indian Bank Healthcare Plus 7. IOB Healthcare Plus 8. k Bank Healthcare Plus 9. Saral Suraksha Bima, USGI 10. Senior Citizen Health Insurance 11. Super Healthcare Insurance | Kasturi Desai\Product Development\Airoli | Completed | Farooq | 31/04/2022 | 2022-05-06 | 2022-05-06 | Unique | 1. Apat Suraksha – Done 2. Arogya Sanjeevani Policy – Done 3. Corona Kavach Policy – Done 4. Critical Illness Policy – Done 5. Hospital Daily Cash– Not Done Reason: Saral Suraksha Bima FAQ is there in excel 6. Indian Bank Healthcare Plus – Done 7. IOB Healthcare Plus – Done 8. k Bank Healthcare Plus – Done 9. Saral Suraksha Bima, USGI – Done 10. Senior Citizen Health Insurance – Done 11. Super Healthcare Insurance – Not Done Reason: Arogya Sanjeevani Policy FAQ is there in excel
20 | 2022-04-30 | Uploading of documents on website | Add Add-ons to following commercial products: Universal Sompo- Bharat Sookshma Udyam Suraksha Universal Sompo - Bharat Laghu Udyam Suraksha Universal Sompo - Bharat Griha Raksha | Dipti Jaiprakashnarain Saxena | Completed | Farooq | 31/04/2022 | 2022-05-02 | 2022-05-02 | Unique